## Experiment Plan
ID | Experiment | Rank r | τ_init | τ_final | Gate k | Sparsity λ | Tokens | Hardware | Est. Time | Key Metric | Purpose / Hypothesis
🔍 SANITY CHECKS (run first, validate pipeline)
S0 | Dense baseline (no predictor) | — | — | — | — | — | 0 | A40×1 | 10 min | NLL_base | Record OLMo2-1B dense NLL on eval set. All experiments must beat this.
S1 | Predictor → identity init | 32 | 5 | 5 | 5 | 0 | 100M | A40×1 | 2 hrs | NLL ≈ NLL_base | Verify init reproduces dense topology. NLL should match S0 within 1%.
S2 | Gradient flow check | 32 | 2 | 2 | 5 | 0 | 500M | A40×1 | 8 hrs | NLL < NLL_base? | Unlock predictor, train briefly. Any NLL drop = gradient flows correctly.
⚙️ PHASE 1 CORE (main training runs)
P1 | Phase 1 — default config | 32 | 5 | 0.2 | 5 | 0→0.01 | 5B | A40×4 | ~4 days | NLL, sparsity | Main run. τ cosine anneal. λ linear ramp from 2B tokens onward.
P2 | Phase 1 — extended | 32 | 5 | 0.2 | 5 | 0→0.01 | 10B | A40×4 | ~7 days | NLL, sparsity | If P1 still improving at 5B, continue. Check diminishing returns.
📊 ABLATION: Rank r (expressiveness vs. compression)
A1 | Rank r = 8 | 8 | 5 | 0.2 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, sparsity | Very compressed. Can 8 dims capture useful topology variation?
A2 | Rank r = 16 | 16 | 5 | 0.2 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, sparsity | Middle ground.
A3 | Rank r = 64 | 64 | 5 | 0.2 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, sparsity | More expressive. Check if overfitting or instability appears.
A4 | Full rank (no decomposition) | 256 | 5 | 0.2 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, sparsity | Upper bound on expressiveness. Expensive predictor output.
🌡️ ABLATION: Temperature schedule
A5 | No annealing (constant τ=1) | 32 | 1 | 1 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, A entropy | Perpetually soft. Does it still learn meaningful structure?
A6 | Aggressive anneal (τ: 5→0.05) | 32 | 5 | 0.05 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, A entropy | Nearly hard binary at end. Check if too aggressive → training instability.
A7 | Slow anneal (τ: 10→1.0) | 32 | 10 | 1 | 5 | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, A entropy | Very soft throughout. More exploration, less commitment.
✂️ ABLATION: Sparsity regularization λ
A8 | No sparsity (λ=0 throughout) | 32 | 5 | 0.2 | 5 | 0 | 2B | A40×4 | ~1.5 days | NLL, density | Pure NLL optimization. How sparse does it get naturally?
A9 | High sparsity (λ=0→0.05) | 32 | 5 | 0.2 | 5 | 0→0.05 | 2B | A40×4 | ~1.5 days | NLL, density | Strong pruning pressure. NLL-sparsity tradeoff frontier.
🚪 ABLATION: Cascading gate
A10 | No cascading gate | 32 | 5 | 0.2 | — | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, dead heads | Without gate constraint. Do dead heads appear with outgoing edges?
A11 | Learnable k (init=5) | 32 | 5 | 0.2 | 5→? | 0→0.01 | 2B | A40×4 | ~1.5 days | NLL, final k | Let model decide gate sharpness. Track learned k value.
🔬 ANALYSIS EXPERIMENTS (run after best config found)
X1 | Topology variance analysis | best | best | best | best | best | — | A40×1 | 2 hrs | Var(A) per-ctx | Feed diverse contexts, measure A variance. Low var = context-independent = bad.
X2 | Domain-specific topology | best | best | best | best | best | — | A40×1 | 2 hrs | A clusters | Compare A on code vs. math vs. prose. Do different domains activate different DAGs?
X3 | Topology→NLL sensitivity | best | best | best | best | best | — | A40×1 | 4 hrs | ΔNLL | Randomly perturb 10%/20%/50% of A edges. How much does NLL degrade?
🚀 PHASE 2 (after Phase 1 validated)
P2a | Phase 2 — joint training | best | best→0.1 | 0.1 | best | reduce | 20B | A100×4 | ~6 days | NLL, ppl | Unfreeze OLMo. Diff LR: OLMo 3e-5, Predictor 1e-4.
P2b | Phase 2 — extended CPT | best | best→0.1 | 0.1 | best | reduce | 50B | A100×4 | ~15 days | NLL, ppl | Full CPT if 20B shows improvement. Monitor collapse (A variance).

## Timeline
Week | Experiments | Hardware | GPU-hours | Checkpoint / Decision
W1 | S0, S1, S2 (sanity checks) | A40×1 | ~12h | GATE: pipeline works, gradient flows, init matches dense NLL
W2 | A1–A4 (rank ablation) | A40×4 | ~144h | DECISION: choose rank r*
W3 | A5–A7 (τ ablation) | A40×4 | ~108h | DECISION: choose τ schedule*
W3 | A8–A9 (λ ablation, parallel) | A40×4 | (shared) | DECISION: choose λ*
W4 | A10–A11 (gate ablation) | A40×4 | ~72h | DECISION: gate on/off, fixed or learnable k*
W5–6 | P1 (main Phase 1, best config, 5B) | A40×4 | ~384h | GATE: NLL < dense baseline on eval set
W6 | P2 (extend to 10B if P1 still improving) | A40×4 | +384h | Optional. Check diminishing returns curve.
W7 | X1–X3 (analysis) | A40×1 | ~8h | INSIGHT: topology is context-dependent, domain-specific
W8–10 | P2a (Phase 2 joint training, 20B) | A100×4 | ~576h | GATE: co-trained model NLL < Phase 1 frozen model
W10–14 | P2b (extended CPT 50B, if warranted) | A100×4 | ~1440h | Final model checkpoint

## Metrics
Metric | What to Log | Frequency | Alert Condition
Eval NLL | NLL on held-out set (same eval set across all runs) | Every 500 steps | NLL > dense baseline after 1B tokens = something wrong
Train NLL | Training loss curve | Every step | Divergence or sudden spike
A mean density | mean(A) — avg edge weight | Every 500 steps | Density stuck at initial value = predictor not learning
A per-context variance | Var(A) across different contexts in eval batch | Every 2000 steps | Var → 0 means context-independent (collapse)
A entropy | Per-edge entropy: -p·log(p)-(1-p)·log(1-p) | Every 2000 steps | Tracks soft→hard transition during τ anneal
Gate activations | Distribution of gⱼ values across all heads | Every 2000 steps | All gates ≈ 1 = gate not doing anything useful
Head pruning rate | Fraction of heads with row-sum(A) < 0.1 | Every 2000 steps | > 50% pruned early = too aggressive
Layer utilization | Per-layer average density | Every 2000 steps | Entire layer pruned = check if intentional or collapse
Predictor gradient norm | Gradient norm of decoder parameters | Every step | Vanishing or exploding gradients
τ (temperature) | Current τ value | Every step | Verify anneal schedule executing correctly
OLMo gradient norm (Phase 2) | Gradient norm of OLMo parameters | Every step | Only in Phase 2. Large spikes = instability
A vs. dense NLL gap | NLL_predicted_topology - NLL_dense | Every 2000 steps | Core success metric. Must be ≤ 0.